## Readiness Dashboard
TMK IT Solutions LLP — Franchise Launch Readiness Dashboard
Master 12-Workstream Readiness Tracker ¦ Version 1.0.0 ¦ Updated 2026-10-26
EXECUTIVE READINESS KPIS
Metric Description | Value | Notes & Status Interpretation
Total Program Tasks |  | Total itemized deliverables across 12 workstreams
Approved / Verified Tasks |  | Formally verified deliverables meeting acceptance criteria
In Progress / Draft Tasks |  | Active work underway across business and engineering units
Not Started Tasks |  | Post-launch or milestone deliverables scheduled for future waves
Active Critical Blockers |  | Systemic defects or unvetted contracts that veto gate passage
Launch Readiness Completion % |  | Weighted percentage of verified deliverables vs total scope
SIX SEQUENTIAL LAUNCH GATES
Gate ID | Gate Name | Target Date | Current Status | Workstreams Governed
GATE-1 | Gate 1: Business Model Approved | 2026-11-15 | Gate Cleared | Business Model & Commercial Strategy, Finance, Banking & Accounting
GATE-2 | Gate 2: Legal & Financial Readiness | 2026-12-01 | In Progress | Legal, Regulatory & Intellectual Property, Finance, Banking & Accounting
GATE-3 | Gate 3: Product & Delivery Readiness | 2026-12-15 | In Progress | Six-Product Sales Readiness, Central Delivery & Customer Support
GATE-4 | Gate 4: Franchise Recruitment Readiness | 2027-01-05 | In Progress | Franchise Recruitment & Marketing, Partner Onboarding Documents
GATE-5 | Gate 5: Pilot Launch Readiness | 2027-01-20 | Pending | Franchise Operations & SOPs, Franchise Management Technology, Training & Certification, Pilot Launch & Final Approval
GATE-6 | Gate 6: National Expansion Approval | 2027-04-30 | Pending | Governance & Performance Monitoring, Pilot Launch & Final Approval

## Workstream Summary
TMK IT Solutions LLP — 12-Workstream Readiness Summary
Dynamic aggregation of deliverables, completion counts, and readiness percentage by domain
# | Workstream Name | Total Tasks | Approved / Verified | In Progress / Draft | Not Started | Completion %
1 | Business Model & Commercial Strategy
2 | Legal, Regulatory & Intellectual Property
3 | Six-Product Sales Readiness
4 | Finance, Banking & Accounting
5 | Franchise Operations & SOPs
6 | Franchise Management Technology
7 | Franchise Recruitment & Marketing
8 | Training & Certification
9 | Central Delivery & Customer Support
10 | Partner Onboarding Documents
11 | Governance & Performance Monitoring
12 | Pilot Launch & Final Approval
TOTAL ALL WORKSTREAMS

## Owner Summary
TMK IT Solutions LLP — Accountable Owner Task Summary
Resource allocation and task completion by responsible role
Role / Responsible Owner | Domain Focus | Total Tasks Assigned | Verified / Approved | In Progress / Draft | Overdue / Blocked
Analyst 1 | Business Strategy, Research, Documentation & Collateral
Analyst 2 | Financial Modeling, Analytics, Schemas & Excel Math
Legal Counsel | Franchise Agreements, Trademark Licensing & Regulatory Review
Lead Software Architect | 6 Software Demo Sandboxes, Cloud HA, RBAC & Provisioning
Finance Director / CA | Banking Escrow, GST Pass-Through Tax & Solvency Verification
Franchise Operations Lead | SOP Handbook, Training Curriculum, Recruitment & Support SLAs
Managing Partner | Executive Decisions, Pilot Agreements & Expansion Gate Approvals
TOTAL ALL ROLES

## Master Checklist
TMK IT Solutions LLP — Master 12-Workstream Launch Readiness Checklist
Complete task inventory, ownership RACI, status tracking, launch gating, and blocker registry
Task ID | Workstream | Title | Description | Priority | Owner Role | Status | Classification | Reviewer Role | Approval Authority | Target Date | Overdue Indicator | Dependencies | Launch Gate | Is Blocker? | Related Document
FLR-BMS-001 | Business Model & Commercial Strategy | FOFO Business Model Specification & RACI Architecture | Formulate comprehensive specification of Franchise Owned, Franchise Operated (FOFO) commercial structure, capital division, and operational RACI matrix. | Critical | Analyst 1 | Document Approved | Business research and modeling | Analyst 2 | Managing Partner | 2026-10-26 |  |  | Gate 1: Business Model Approved | TRUE | clients/tmk-it-solutions/franchise-model/fofo-operating-model.md
FLR-BMS-002 | Business Model & Commercial Strategy | Franchise Fee Structure & Promotional Tier Policy | Establish policy for promotional ₹25,000 joining fee (first 10 units) and standard ₹50,000 fee with documented renewal terms. | High | Analyst 1 | Document Approved | Business research and modeling | Analyst 2 | Managing Partner | 2026-10-26 |  | FLR-BMS-001 | Gate 1: Business Model Approved | FALSE | clients/tmk-it-solutions/franchise-model/fee-structure.md
FLR-BMS-003 | Business Model & Commercial Strategy | 40:60 Net Revenue Sharing Rules & Machine Config | Define contractual revenue-sharing percentages (40% Franchisee : 60% TMK) and machine-readable JSON configuration. | Critical | Analyst 2 | Document Approved | Finance and accounting | Analyst 1 | Finance Director / CA | 2026-10-26 |  | FLR-BMS-001 | Gate 1: Business Model Approved | TRUE | clients/tmk-it-solutions/franchise-model/revenue-sharing-rules.md, clients/tmk-it-solutions/franchise-model/revenue-sharing-config.json
FLR-BMS-004 | Business Model & Commercial Strategy | Six-Product Market Demand Brief & TAM/SAM/SOM Sizing | Quantify total addressable market and serviceable opportunity for TMK software portfolio across Tier-2/3 Indian markets. | High | Analyst 1 | Document Approved | Business research and modeling | Analyst 2 | Practice Lead | 2026-10-26 |  |  | Gate 1: Business Model Approved | FALSE | clients/tmk-it-solutions/research/six-product-demand-analysis.md
FLR-BMS-005 | Business Model & Commercial Strategy | Taluka-Based Territory Segmentation Strategy | Define territorial boundaries utilizing sub-district (Taluka / Tehsil) administrative divisions with TOS scoring. | High | Analyst 1 | Document Approved | Business research and modeling | Analyst 2 | Practice Lead | 2026-10-26 |  | FLR-BMS-004 | Gate 1: Business Model Approved | FALSE | clients/tmk-it-solutions/research/taluka-based-territory-strategy.md
FLR-BMS-006 | Business Model & Commercial Strategy | Three-Year Expansion Growth Vision & Wave Rollout Plan | Establish 36-month expansion trajectory: Wave 1 Pilot (3 units), Wave 2 Western Maharashtra (15 units), Wave 3 Statewide (50 units). | Medium | Analyst 1 | Document Approved | Documentation and presentation | Managing Partner | Managing Partner | 2026-10-26 |  | FLR-BMS-005 | Gate 1: Business Model Approved | FALSE | clients/tmk-it-solutions/sales-marketing/three-year-growth-vision.md
FLR-LGL-001 | Legal, Regulatory & Intellectual Property | Master Franchise Agreement Drafting | Author complete legal agreement draft specifying license grant, payment terms, territory rules, audit rights, and termination. | Critical | Analyst 1 | Document Created | Documentation and presentation | Legal Counsel | Legal Counsel | 2026-10-26 |  | FLR-BMS-001, FLR-BMS-003 | Gate 2: Legal & Financial Readiness | TRUE | clients/tmk-it-solutions/legal-drafts/franchise-agreement-draft.md
FLR-LGL-002 | Legal, Regulatory & Intellectual Property | Corporate Legal Counsel Review & Compliance Certification | Formal vetting by independent corporate legal counsel under Indian Contract Act, Specific Relief Act, and Consumer Protection laws. | Critical | Legal Counsel | In Progress | Legal and regulatory review | Managing Partner | Legal Counsel | 2026-12-01 |  | FLR-LGL-001 | Gate 2: Legal & Financial Readiness | TRUE | clients/tmk-it-solutions/legal-drafts/franchise-agreement-draft.md
FLR-LGL-003 | Legal, Regulatory & Intellectual Property | Territory Protection Policy & Anti-Encroachment Covenant | Draft formal legal policy governing 90-day Deal Registration Locks, territorial exclusivity boundaries, and dispute arbitration. | High | Analyst 1 | Document Created | Documentation and presentation | Legal Counsel | Legal Counsel | 2026-10-26 |  | FLR-BMS-005 | Gate 2: Legal & Financial Readiness | FALSE | clients/tmk-it-solutions/legal-drafts/territory-policy-draft.md
FLR-LGL-004 | Legal, Regulatory & Intellectual Property | Trademark & Brand Usage License Guidelines | Draft trademark license terms specifying permitted use of TMK IT Solutions logos, trade dress, and signage standards. | High | Analyst 1 | Document Created | Documentation and presentation | Legal Counsel | Legal Counsel | 2026-10-26 |  |  | Gate 2: Legal & Financial Readiness | FALSE | clients/tmk-it-solutions/legal-drafts/brand-usage-policy-draft.md
FLR-LGL-005 | Legal, Regulatory & Intellectual Property | Franchise Renewal, Buyback & Termination Policies | Formulate legal policies governing contract renewals, performance hurdle benchmarks, voluntary surrender, and default termination. | High | Analyst 1 | Document Created | Documentation and presentation | Legal Counsel | Legal Counsel | 2026-10-26 |  | FLR-LGL-001 | Gate 2: Legal & Financial Readiness | FALSE | clients/tmk-it-solutions/legal-drafts/franchise-renewal-policy-draft.md, clients/tmk-it-solutions/legal-drafts/franchise-termination-policy-draft.md
FLR-LGL-006 | Legal, Regulatory & Intellectual Property | Non-Disclosure & Mutual Confidentiality Agreement | Draft bilateral NDA executed with prospective franchise candidates prior to sharing proprietary product documentation. | Medium | Analyst 1 | Document Created | Documentation and presentation | Legal Counsel | Legal Counsel | 2026-10-26 |  |  | Gate 2: Legal & Financial Readiness | FALSE | clients/tmk-it-solutions/legal-drafts/confidentiality-agreement-draft.md
FLR-PRD-001 | Six-Product Sales Readiness | Cloud Enterprise ERP Commercial Profile & Spec | Document product feature breakdown, target MSME buyer personas, pricing tiers, and delivery model for prd-01 Enterprise ERP. | High | Analyst 1 | Document Approved | Documentation and presentation | Lead Software Architect | Lead Software Architect | 2026-10-26 |  |  | Gate 3: Product & Delivery Readiness | FALSE | clients/tmk-it-solutions/products/devops-automation.md
FLR-PRD-002 | Six-Product Sales Readiness | School & College Management ERP Commercial Profile | Document educational software modules (admissions, fee billing, exams) and school demographic targeting. | High | Analyst 1 | Document Approved | Documentation and presentation | Lead Software Architect | Lead Software Architect | 2026-10-26 |  |  | Gate 3: Product & Delivery Readiness | FALSE | clients/tmk-it-solutions/products/school-college-erp.md
FLR-PRD-003 | Six-Product Sales Readiness | OMR Examination Software Commercial Profile | Document optical mark recognition software pricing, offline scanning hardware compatibility, and school evaluation workflows. | Medium | Analyst 1 | Document Approved | Documentation and presentation | Lead Software Architect | Lead Software Architect | 2026-10-26 |  |  | Gate 3: Product & Delivery Readiness | FALSE | clients/tmk-it-solutions/products/omr-software.md
FLR-PRD-004 | Six-Product Sales Readiness | Property Management ERP Commercial Profile | Document housing society, commercial real estate, and tenant maintenance billing software modules. | Medium | Analyst 1 | Document Approved | Documentation and presentation | Lead Software Architect | Lead Software Architect | 2026-10-26 |  |  | Gate 3: Product & Delivery Readiness | FALSE | clients/tmk-it-solutions/products/property-management-erp.md
FLR-PRD-005 | Six-Product Sales Readiness | Invoicing & Billing App (Web + Mobile) Commercial Profile | Document lightweight GST billing application for retail shops and micro-merchants. | High | Analyst 1 | Document Approved | Documentation and presentation | Lead Software Architect | Lead Software Architect | 2026-10-26 |  |  | Gate 3: Product & Delivery Readiness | FALSE | clients/tmk-it-solutions/products/invoicing-app-web.md
FLR-PRD-006 | Six-Product Sales Readiness | Sales CRM Platform Commercial Profile | Document lead pipeline management, WhatsApp integration, and sales telemetry for regional businesses. | High | Analyst 1 | Document Approved | Documentation and presentation | Lead Software Architect | Lead Software Architect | 2026-10-26 |  |  | Gate 3: Product & Delivery Readiness | FALSE | clients/tmk-it-solutions/products/sales-crm.md
FLR-PRD-007 | Six-Product Sales Readiness | Live Multi-Tenant Cloud Demonstration Sandbox | Deploy stable cloud demonstration instances for all 6 products pre-populated with synthetic demonstration data. | Critical | Lead Software Architect | In Progress | Product engineering | Managing Partner | Lead Software Architect | 2026-12-15 |  | FLR-PRD-001, FLR-PRD-002, FLR-PRD-003, FLR-PRD-004, FLR-PRD-005, FLR-PRD-006 | Gate 3: Product & Delivery Readiness | TRUE | clients/tmk-it-solutions/products/products-catalog.json
FLR-PRD-008 | Six-Product Sales Readiness | Competitor Benchmarking & Sales Battlecards | Equip partners with competitive comparisons against TallyPrime, Marg ERP, Teachmint, Vyapar, and Zoho. | High | Analyst 1 | Document Approved | Business research and modeling | Analyst 2 | Practice Lead | 2026-10-26 |  |  | Gate 3: Product & Delivery Readiness | FALSE | clients/tmk-it-solutions/research/competitor-landscape.md
FLR-FIN-001 | Finance, Banking & Accounting | Financial Assumptions Master Config & Schema Compliance | Establish validated assumptions.json governing CapEx, monthly fixed OpEx, fee schedules, tax rates, and scenarios. | Critical | Analyst 2 | Document Approved | Finance and accounting | Finance Director / CA | Finance Director / CA | 2026-10-26 |  |  | Gate 1: Business Model Approved | TRUE | clients/tmk-it-solutions/financial-models/assumptions.json
FLR-FIN-002 | Finance, Banking & Accounting | Dynamic 10-Sheet Excel Financial Model Generation | Generate dynamic, formula-linked openpyxl Excel financial model with uppercase formulas and zero hardcoded numbers. | Critical | Analyst 2 | Process Implemented | Finance and accounting | Finance Director / CA | Finance Director / CA | 2026-10-26 |  | FLR-FIN-001 | Gate 1: Business Model Approved | TRUE | clients/tmk-it-solutions/financial-models/tmk_it_solutions_franchise_financial_model.xlsx
FLR-FIN-003 | Finance, Banking & Accounting | 36-Month P&L Projections & Break-Even Analysis Summary | Document narrative summary of monthly cash flows, unit break-even requirements (2 contracts/mo), and payback timeline. | High | Analyst 2 | Document Approved | Documentation and presentation | Analyst 1 | Practice Lead | 2026-10-26 |  | FLR-FIN-002 | Gate 1: Business Model Approved | FALSE | clients/tmk-it-solutions/financial-models/financial-projections-summary.md
FLR-FIN-004 | Finance, Banking & Accounting | Statutory Pass-Through Tax Isolation Engine (18% GST) | Verify that all financial models and billing tools isolate 18% GST from gross billing before computing commission splits. | Critical | Analyst 2 | Process Verified | Finance and accounting | Finance Director / CA | Finance Director / CA | 2026-10-26 |  | FLR-FIN-001 | Gate 2: Legal & Financial Readiness | TRUE | tools/financial-modeling/calculator.py
FLR-FIN-005 | Finance, Banking & Accounting | Franchisee Working Capital Reserve Verification Standard | Codify mandatory liquid capital cushion requirement (₹50,000–₹1,00,000 covering 4–6 months overhead) in assumptions. | High | Analyst 2 | Document Approved | Finance and accounting | Finance Director / CA | Finance Director / CA | 2026-10-26 |  | FLR-FIN-001 | Gate 2: Legal & Financial Readiness | TRUE | clients/tmk-it-solutions/research/franchisee-investment-feasibility.md
FLR-FIN-006 | Finance, Banking & Accounting | Dedicated Franchisor Escrow & Commission Settlement Account | Establish dedicated commercial bank account and automated escrow disbursement procedure for partner revenue splits. | Critical | Finance Director / CA | In Progress | Finance and accounting | Managing Partner | Managing Partner | 2026-12-01 |  | FLR-FIN-004 | Gate 2: Legal & Financial Readiness | TRUE | clients/tmk-it-solutions/legal-drafts/revenue-sharing-policy-draft.md
FLR-OPS-001 | Franchise Operations & SOPs | Franchisee Operations Handbook & Facility Launch SOP | Author operational handbook detailing office setup, brand signage, daily opening/closing procedures, and customer onboarding. | High | Analyst 1 | Document Created | Documentation and presentation | Franchise Operations Lead | Franchise Operations Lead | 2026-10-26 |  |  | Gate 5: Pilot Launch Readiness | FALSE | clients/tmk-it-solutions/operations/franchise-operations-handbook.md
FLR-OPS-002 | Franchise Operations & SOPs | Customer Support SLA & Engineering Escalation Matrix | Establish formal service level agreement defining resolution windows: P1 Critical (< 2h), P2 Major (< 8h), P3 Minor (< 24h). | Critical | Analyst 1 | Document Approved | Franchise operations | Lead Software Architect | Lead Software Architect | 2026-10-26 |  |  | Gate 3: Product & Delivery Readiness | TRUE | clients/tmk-it-solutions/operations/support-sla-matrix.md
FLR-OPS-003 | Franchise Operations & SOPs | Franchise Unit Physical Onboarding Journey & Milestones | Document sequential 30-day onboarding journey from contract signing to office launch and commercial go-live. | High | Analyst 1 | Document Approved | Franchise operations | Franchise Operations Lead | Franchise Operations Lead | 2026-10-26 |  | FLR-OPS-001 | Gate 5: Pilot Launch Readiness | FALSE | clients/tmk-it-solutions/franchise-model/onboarding-journey.md
FLR-OPS-004 | Franchise Operations & SOPs | Client Onboarding & Data Migration Protocol | Standardize standard operating procedure for migrating customer legacy data (Tally XML, Excel sheets) into TMK Cloud ERP. | Medium | Franchise Operations Lead | In Progress | Franchise operations | Lead Software Architect | Lead Software Architect | 2026-12-15 |  | FLR-PRD-001 | Gate 5: Pilot Launch Readiness | FALSE | clients/tmk-it-solutions/operations/franchise-operations-handbook.md
FLR-OPS-005 | Franchise Operations & SOPs | Franchise Risk Register & Mitigation Playbooks | Maintain exhaustive 5x5 risk scoring matrix covering partner default, regulatory change, and competition risks. | High | Analyst 2 | Document Approved | Management approval | Managing Partner | Managing Partner | 2026-10-26 |  |  | Gate 5: Pilot Launch Readiness | FALSE | clients/tmk-it-solutions/risks/risk-register.md
FLR-TEC-001 | Franchise Management Technology | Central Partner Portal Architecture & Specification | Specify multi-tenant partner dashboard architecture for commission tracking, lead registration, and support ticketing. | High | Lead Software Architect | Document Created | Technology implementation | Managing Partner | Lead Software Architect | 2026-10-26 |  |  | Gate 5: Pilot Launch Readiness | FALSE | platform/architecture/system-architecture.md
FLR-TEC-002 | Franchise Management Technology | CRM Lead Protection & 90-Day Deal Registration Engine | Implement automated 90-day prospect locking algorithm in CRM to prevent partner encroachment and channel conflict. | Critical | Lead Software Architect | In Progress | Technology implementation | Franchise Operations Lead | Franchise Operations Lead | 2026-12-20 |  | FLR-TEC-001, FLR-LGL-003 | Gate 5: Pilot Launch Readiness | TRUE | clients/tmk-it-solutions/legal-drafts/territory-policy-draft.md
FLR-TEC-003 | Franchise Management Technology | Automated Software License Key Provisioning Workflow | Automate cloud deployment and cryptographic license key generation upon invoice settlement. | High | Lead Software Architect | In Progress | Product engineering | Finance Director / CA | Lead Software Architect | 2027-01-05 |  | FLR-TEC-001 | Gate 5: Pilot Launch Readiness | FALSE | clients/tmk-it-solutions/products/products-catalog.json
FLR-TEC-004 | Franchise Management Technology | Cloud Infrastructure 99.9% High-Availability Deployment | Deploy resilient containerized Kubernetes / VPS infrastructure with automated daily snapshots and DDoS protection. | High | Lead Software Architect | Process Implemented | Technology implementation | Managing Partner | Lead Software Architect | 2026-10-26 |  |  | Gate 3: Product & Delivery Readiness | FALSE | clients/tmk-it-solutions/operations/support-sla-matrix.md
FLR-TEC-005 | Franchise Management Technology | Role-Based Access Control (RBAC) & Tenant Security Audit | Enforce strict JWT / OAuth2 authentication ensuring franchisees access only their own territory accounts. | Critical | Lead Software Architect | Process Verified | Technology implementation | Managing Partner | Lead Software Architect | 2026-10-26 |  | FLR-TEC-001 | Gate 5: Pilot Launch Readiness | TRUE | platform/security/security-policy.md
FLR-MKT-001 | Franchise Recruitment & Marketing | Franchise Opportunity Pitch Deck & PPTX Presentation | Build high-impact 10-slide investor presentation detailing business model, unit economics, 6 products, and revenue potential. | Critical | Analyst 1 | Document Approved | Documentation and presentation | Managing Partner | Managing Partner | 2026-10-26 |  | FLR-BMS-001, FLR-FIN-003 | Gate 4: Franchise Recruitment Readiness | TRUE | clients/tmk-it-solutions/presentations/franchise-opportunity-pitch-deck.md, clients/tmk-it-solutions/presentations/franchise-opportunity-pitch-deck.pptx
FLR-MKT-002 | Franchise Recruitment & Marketing | Franchise Recruitment Commercial Brochure (4-Page) | Design print-ready marketing brochure highlighting software demand, promotional fee tier, and partner profile. | High | Analyst 1 | Document Approved | Documentation and presentation | Analyst 2 | Practice Lead | 2026-10-26 |  | FLR-MKT-001 | Gate 4: Franchise Recruitment Readiness | FALSE | clients/tmk-it-solutions/sales-marketing/franchise-brochure.md
FLR-MKT-003 | Franchise Recruitment & Marketing | Institutional Franchise Investment Prospectus | Author comprehensive investment document detailing corporate history, commercial contract terms, unit economics, and risk factors. | Critical | Analyst 1 | Document Approved | Documentation and presentation | Legal Counsel | Managing Partner | 2026-10-26 |  | FLR-BMS-001, FLR-FIN-002 | Gate 4: Franchise Recruitment Readiness | TRUE | clients/tmk-it-solutions/sales-marketing/franchise-prospectus.md
FLR-MKT-004 | Franchise Recruitment & Marketing | Candidate Investor FAQ with Non-Guaranteed Return Disclaimers | Provide answers to 20+ common partner objections regarding CapEx, sales cycles, support escalations, and territory boundaries. | High | Analyst 1 | Document Approved | Documentation and presentation | Legal Counsel | Practice Lead | 2026-10-26 |  | FLR-MKT-003 | Gate 4: Franchise Recruitment Readiness | FALSE | clients/tmk-it-solutions/sales-marketing/franchise-faq.md
FLR-MKT-005 | Franchise Recruitment & Marketing | FOFO Architecture Infographic & Revenue Model Visualizer | Create graphical specifications depicting money flows, 18% GST deduction, and 40:60 revenue splits. | Medium | Analyst 1 | Document Approved | Documentation and presentation | Analyst 2 | Practice Lead | 2026-10-26 |  | FLR-BMS-003 | Gate 4: Franchise Recruitment Readiness | FALSE | clients/tmk-it-solutions/sales-marketing/fofo-infographic-spec.md, clients/tmk-it-solutions/sales-marketing/revenue-sharing-infographic-spec.md
FLR-MKT-006 | Franchise Recruitment & Marketing | Digital Lead Capture Funnel & Prospect Evaluation Rubric | Establish landing page copy, qualification scorecard, and candidate screening criteria for recruitment marketing. | High | Franchise Operations Lead | In Progress | Franchise operations | Managing Partner | Franchise Operations Lead | 2026-12-10 |  | FLR-MKT-002 | Gate 4: Franchise Recruitment Readiness | FALSE | clients/tmk-it-solutions/sales-marketing/franchise-application-form.md
FLR-TRN-001 | Training & Certification | 10-Day Franchisee Onboarding Training Curriculum | Establish comprehensive 10-day syllabus covering products, sales pitching, office setup, and support escalations. | Critical | Franchise Operations Lead | Document Approved | Franchise operations | Analyst 1 | Franchise Operations Lead | 2026-10-26 |  | FLR-PRD-001, FLR-OPS-001 | Gate 5: Pilot Launch Readiness | TRUE | clients/tmk-it-solutions/operations/franchise-training-curriculum.md
FLR-TRN-002 | Training & Certification | Sales Executive Product Demonstration Scripts & Playbook | Create 5-step demonstration scripts, objection battlecards, and sales kits for all software offerings. | High | Analyst 1 | Document Created | Documentation and presentation | Lead Software Architect | Practice Lead | 2026-10-26 |  | FLR-TRN-001 | Gate 5: Pilot Launch Readiness | FALSE | templates/product-demonstrations/product-demo-guide.template.md
FLR-TRN-003 | Training & Certification | Operations Manual Examination & Passing Rubric | Design 100-question written examination requiring 80% passing grade on commercial terms, software, and compliance. | High | Franchise Operations Lead | In Progress | Franchise operations | Managing Partner | Franchise Operations Lead | 2026-12-20 |  | FLR-TRN-001 | Gate 5: Pilot Launch Readiness | FALSE | clients/tmk-it-solutions/operations/franchise-training-curriculum.md
FLR-TRN-004 | Training & Certification | Formal Partner Certification Accreditation Package | Establish formal certificate of accreditation, partner badge, and authorization credentials upon passing training. | Medium | Franchise Operations Lead | In Progress | Documentation and presentation | Managing Partner | Managing Partner | 2027-01-10 |  | FLR-TRN-003 | Gate 5: Pilot Launch Readiness | FALSE | templates/training/franchisee-training-curriculum.template.md
FLR-DEL-001 | Central Delivery & Customer Support | Central Engineering Deployment Capacity Verification | Audit central engineering staff capacity to ensure team can deliver 15+ concurrent client deployments monthly. | Critical | Lead Software Architect | Process Implemented | Product engineering | Managing Partner | Lead Software Architect | 2026-10-26 |  | FLR-OPS-002 | Gate 3: Product & Delivery Readiness | TRUE | clients/tmk-it-solutions/operations/support-sla-matrix.md
FLR-DEL-002 | Central Delivery & Customer Support | Cloud Server Infrastructure Monitoring & Disaster Recovery | Implement automated database backup, regional replication, and 15-minute RTO disaster recovery protocol. | High | Lead Software Architect | Process Implemented | Technology implementation | Managing Partner | Lead Software Architect | 2026-10-26 |  |  | Gate 3: Product & Delivery Readiness | FALSE | platform/architecture/system-architecture.md
FLR-DEL-003 | Central Delivery & Customer Support | Ticketing System Multi-Tenant Queue Configuration | Configure support ticketing queues with automated routing based on customer subscription tier and severity. | High | Lead Software Architect | In Progress | Technology implementation | Franchise Operations Lead | Franchise Operations Lead | 2026-12-15 |  | FLR-OPS-002 | Gate 3: Product & Delivery Readiness | FALSE | clients/tmk-it-solutions/operations/support-sla-matrix.md
FLR-DEL-004 | Central Delivery & Customer Support | End-Client Customer Satisfaction (CSAT/NPS) Survey System | Deploy automated 30-day post-onboarding satisfaction survey to benchmark end-user adoption and support quality. | Medium | Franchise Operations Lead | In Progress | Franchise operations | Analyst 1 | Franchise Operations Lead | 2027-01-15 |  | FLR-DEL-003 | Gate 3: Product & Delivery Readiness | FALSE | templates/dashboards/franchise-kpi-dashboard.template.md
FLR-ONB-001 | Partner Onboarding Documents | Franchise Application & Due Diligence Questionnaire | Create comprehensive application form capturing candidate business background, commercial references, and territory choice. | High | Analyst 1 | Document Approved | Documentation and presentation | Franchise Operations Lead | Franchise Operations Lead | 2026-10-26 |  |  | Gate 4: Franchise Recruitment Readiness | FALSE | clients/tmk-it-solutions/sales-marketing/franchise-application-form.md
FLR-ONB-002 | Partner Onboarding Documents | Partner KYC Dossier & Background Verification Protocol | Establish formal identity, police verification, credit bureau check (CIBIL $\ge 700$), and commercial reference check process. | High | Franchise Operations Lead | Document Created | Franchise operations | Legal Counsel | Legal Counsel | 2026-10-26 |  | FLR-ONB-001 | Gate 4: Franchise Recruitment Readiness | FALSE | templates/checklists/franchise-due-diligence-questionnaire.template.md
FLR-ONB-003 | Partner Onboarding Documents | Bank Statement Proof-of-Funds Verification Protocol | Verify unencumbered bank balance demonstrating candidate has setup CapEx (₹75k) + minimum ₹50,000 liquid working capital cushion. | Critical | Finance Director / CA | Document Created | Finance and accounting | Managing Partner | Finance Director / CA | 2026-10-26 |  | FLR-FIN-005 | Gate 4: Franchise Recruitment Readiness | TRUE | clients/tmk-it-solutions/research/franchisee-investment-feasibility.md
FLR-ONB-004 | Partner Onboarding Documents | Partner Welcome Kit & Collateral Dispatch SOP | Standardize physical welcome box: acrylic desk plaque, visiting cards, software manuals, marketing standee, and official certificate. | Medium | Franchise Operations Lead | Document Created | Franchise operations | Analyst 1 | Franchise Operations Lead | 2026-10-26 |  | FLR-OPS-003 | Gate 4: Franchise Recruitment Readiness | FALSE | clients/tmk-it-solutions/franchise-model/onboarding-journey.md
FLR-GOV-001 | Governance & Performance Monitoring | 13 Core Franchise KPI Tracking Dashboard Specification | Specify executive telemetry dashboard monitoring sales velocity, EBITDA, renewal retention, and support SLAs across territories. | High | Analyst 2 | Document Approved | Documentation and presentation | Franchise Operations Lead | Practice Lead | 2026-10-26 |  |  | Gate 5: Pilot Launch Readiness | FALSE | templates/dashboards/franchise-kpi-dashboard.template.md
FLR-GOV-002 | Governance & Performance Monitoring | Minimum Quarterly Software License Benchmark Quotas | Codify territory benchmark quotas (e.g. minimum 6 contracts per quarter post-ramp) required to maintain exclusivity. | High | Analyst 2 | Document Approved | Business research and modeling | Managing Partner | Managing Partner | 2026-10-26 |  | FLR-BMS-005 | Gate 5: Pilot Launch Readiness | FALSE | clients/tmk-it-solutions/financial-models/assumptions.json
FLR-GOV-003 | Governance & Performance Monitoring | Franchise Advisory Council (FAC) Governance Charter | Formulate governance framework for collaborative franchisee representation, quarterly sessions, and product roadmap reviews. | Medium | Analyst 1 | Document Created | Documentation and presentation | Managing Partner | Managing Partner | 2026-10-26 |  |  | Gate 6: National Expansion Approval | FALSE | templates/governance/franchise-advisory-council-charter.template.md
FLR-GOV-004 | Governance & Performance Monitoring | Management Decision Register & Policy Revision Log | Maintain immutable audit log recording all formal leadership decisions regarding fee revisions, waivers, and territory adjustments. | High | Analyst 1 | Process Implemented | Management approval | Managing Partner | Managing Partner | 2026-10-26 |  |  | Gate 5: Pilot Launch Readiness | FALSE | clients/tmk-it-solutions/decisions/management-decision-register.md
FLR-GOV-005 | Governance & Performance Monitoring | Formal Approval Matrix Tracking Client Sign-Offs | Maintain centralized ledger of formal deliverable approvals and signing authorities. | Critical | Analyst 1 | Process Implemented | Management approval | Managing Partner | Managing Partner | 2026-10-26 |  |  | Gate 1: Business Model Approved | TRUE | clients/tmk-it-solutions/approvals/approval-matrix.md
FLR-PLT-001 | Pilot Launch & Final Approval | Pilot Territory Demographics & Validation Brief (Pune, Satara, Baramati) | Analyze commercial potential, MSME density, and school counts across the 3 selected Wave 1 pilot territories. | High | Analyst 1 | Document Approved | Business research and modeling | Analyst 2 | Practice Lead | 2026-10-26 |  | FLR-BMS-005 | Gate 5: Pilot Launch Readiness | FALSE | clients/tmk-it-solutions/operations/pilot-launch-protocol.md
FLR-PLT-002 | Pilot Launch & Final Approval | Wave 1 Pilot Launch & Audit Protocol Specification | Establish 30/60/90-day evaluation gates, promotional fee agreements (₹25,000), and governance committee responsibilities. | Critical | Franchise Operations Lead | Document Approved | Franchise operations | Managing Partner | Managing Partner | 2026-10-26 |  | FLR-PLT-001 | Gate 5: Pilot Launch Readiness | TRUE | clients/tmk-it-solutions/operations/pilot-launch-protocol.md
FLR-PLT-003 | Pilot Launch & Final Approval | Selection & Contracting of Initial 3 Pilot Franchise Partners | Vet candidate operators for Pune, Satara, and Baramati; execute pilot agreements with verified working capital cushion. | Critical | Managing Partner | In Progress | Management approval | Legal Counsel | Managing Partner | 2027-01-20 |  | FLR-LGL-002, FLR-ONB-003, FLR-PLT-002 | Gate 5: Pilot Launch Readiness | TRUE | clients/tmk-it-solutions/operations/pilot-launch-protocol.md
FLR-PLT-004 | Pilot Launch & Final Approval | 30-Day Pilot Operational Review & Lead Velocity Audit | Audit physical office setups, initial CRM lead generation velocity, and mock software demo completion for pilot units. | High | Analyst 1 | Not Started | Franchise operations | Franchise Operations Lead | Franchise Operations Lead | 2027-02-28 |  | FLR-PLT-003 | Gate 6: National Expansion Approval | FALSE | clients/tmk-it-solutions/operations/pilot-launch-protocol.md
FLR-PLT-005 | Pilot Launch & Final Approval | 60-Day Pilot Revenue & Commission Reconciliation Audit | Audit first commercial sales, billing generation, 18% GST remittance, and partner commission disbursements. | Critical | Analyst 2 | Not Started | Finance and accounting | Finance Director / CA | Finance Director / CA | 2027-03-31 |  | FLR-PLT-004 | Gate 6: National Expansion Approval | TRUE | clients/tmk-it-solutions/operations/pilot-launch-protocol.md
FLR-PLT-006 | Pilot Launch & Final Approval | 90-Day Pilot Completion Audit & National Expansion Gate Approval | Executive review evaluating pilot sales velocity, CSAT survey scores ($\ge 85\%$), and model financial reconciliation. | Critical | Managing Partner | Not Started | Management approval | Executive Committee | Managing Partner | 2027-04-30 |  | FLR-PLT-005 | Gate 6: National Expansion Approval | TRUE | clients/tmk-it-solutions/operations/pilot-launch-protocol.md
Formulas:
Overdue Indicator = IF(AND([Target Date]<TODAY(), [Status]<>"Document Approved", [Status]<>"Process Verified"), "OVERDUE", "On Track")

## Gates & Blockers
TMK IT Solutions LLP — Launch Gates & Blocker Specifications
Stage-gate entry/exit criteria, non-negotiable blocker definitions, and override policies
STAGE-GATE GOVERNANCE MATRIX
Gate ID | Gate Name | Target Date | Governing Domains | Mandatory Exit Criteria | Approval Authority
Gate 1 | Gate 1: Business Model Approved | 2026-10-26 | Strategy, Pricing & Revenue Sharing | Break-even units verified (2 contracts/mo); payback <= 12 months; formal sign-off. | Managing Partner
Gate 2 | Gate 2: Legal & Financial Readiness | 2026-12-01 | Legal Agreements, Statutory Taxes & Escrow | Master agreement certified by corporate legal counsel; 18% GST pass-through isolated; bank escrow active. | Corporate Legal Counsel & CA
Gate 3 | Gate 3: Product & Delivery Readiness | 2026-12-15 | 6 Software Products, Central SLAs & Cloud | Live demonstration sandboxes active for all 6 products; support SLA matrix approved; 99.9% cloud HA. | Lead Software Architect
Gate 4 | Gate 4: Franchise Recruitment Readiness | 2027-01-05 | Pitch Collateral, Prospectus & Vetting | Institutional prospectus and FAQ completed with disclaimers; partner application form active; proof-of-funds verified. | Head of Recruitment & Counsel
Gate 5 | Gate 5: Pilot Launch Readiness | 2027-01-20 | Operations SOPs, CRM Deal Lock & Training | 10-day training curriculum completed; 90-day CRM deal lock engine active; 3 pilot partner agreements signed. | Director of Operations & CEO
Gate 6 | Gate 6: National Expansion Approval | 2027-04-30 | Pilot Audits, CSAT & Network Gating | 90-day pilot sales velocity reconciled against model; end-customer CSAT >= 85%; board authorization. | Board of Directors / Executive Lead
CRITICAL LAUNCH BLOCKER TAXONOMY (AUTOMATIC VETO CONDITIONS)
Blocker ID | Affected Gates | Defect Title & Root Cause | Impact & Risk | Mandatory Resolution Requirement | Default Status
BLK-001 | Gate 2, Gate 4 | Unvetted Franchise Contract | Regulatory fines, illegal contract claims, partner litigation | Written certification and legal opinion signed by corporate counsel | Active - In Progress
BLK-002 | Gate 2 | Tax Pass-Through Non-Segregation | Illegal GST tax non-compliance, distorted partner commission calculations | Decimal calculator isolates 18% GST before computing 40:60 splits | Resolved - Verified
BLK-003 | Gate 3 | Unstable Software Demo Sandbox | Failed sales presentations, damaged franchisor credibility, zero conversions | Dedicated cloud demo instances deployed with synthetic test data and 99.9% uptime | Active - Staging
BLK-004 | Gate 3, Gate 5 | Undefined Central SLA Escalation | Unresolved software defects, customer churn, partner dissatisfaction | Published SLA matrix with signed engineering commitment for P1 (< 2h) issues | Resolved - Approved
BLK-005 | Gate 4, Gate 5 | Inadequate Partner Working Capital Reserve | Partner insolvency during initial ramp-up, unit abandonment, brand failure | Mandatory bank statement proof-of-funds verification (minimum ₹50k liquid cushion) | Active - Draft Created
BLK-006 | Gate 6 | Unvalidated Pilot Milestone Audit | Premature national rollout of flawed economic or operational model | Completed 90-day pilot revenue audit and CSAT survey (>= 85%) | Pending - Scheduled
BLK-007 | Gate 5 | Absence of CRM Deal Registration Lock | Partner lead poaching, territory disputes, channel cannibalization | Technical enforcement of 90-day prospect protection in central partner portal | Active - Testing